## Sheet1
Process |  | Method |  |  |  |  | Action
Sample
Process Step | What is being Controlled? | How is it Measured? | Size | Frequency | Responsible Party | Where is it Recorded? | Response Plan | Responsible Party
Attendance Reports from automated systems are sent to all stakeholders | Attendance Tracking | Check if the report is sent everyday at 12:00 pm | 1 Report | Every Day | MIS | MIS Tracker | Reach the attendance application vendor and log a ticket | MIS SPOC
Track if SMS service is working for all employees | SMS Service | Check if the roster sms is sent to all employees | 1 Report | Every Thursday | MIS | MIS Tracker | Reach the sms application vendor and log a ticket | MIS SPOC
Track in-time of all supervisors | Login Time of all Supervisors | Check the automated attendance tracker for supervisors | 1 Report | Every Day | Manager | Manager Folder | If the automated attendance tracker fails, approach the MIS team to log a ticket with the vendor | Manager
Provide training to all supervisors to give feedback if their team members arrive late | Supervisor action | Training attendance and training exam scores | 1 Report | Every Month | Manager | Training Folder | If the training is not conducted, approach the training team and report the issue | Manager
Engage team members in team bonding activities | Team Bonding | Check if the monthly team outing budget is used by respective supervisors | 1 Report | Every Month | Manager | Finance Reports | If the team outing budget is not used, seek an explanation from the supervisor | Manager